## Slide 1
Ammonia gas engine readiness timeline — IHI, HD Hyundai, Wärtsilä
Merged: grey = AWS/research_OEM public survey · colour = AWS/comm_OEM commercial decks. Ammonia-fired reciprocating engines only (excludes gas turbines & hydrogen engines).
Confirmed (comm_OEM)
Confirmed (research_OEM)
Unverified / target
Planned / ramp period
Tested / demonstrated
2023
2024
2025
2026
2027
2028
2029
Today, 19 Sep 2026
IHI
18V28ADF dual-fuel (6 MW, land)
Commercial sales from JFY2027
28AGS-AM 100% ammonia engine (land)
Commercialisation from 2028
Same IHI deck also calls this “AGX”, dated 2028–2029 — unresolved internal inconsistency
HD Hyundai
HiMSEN ammonia genset (stationary)
intent stated, no date confirmed
H22CDF-LA dual-fuel (1.4–2.2 MW, marine)
Type Approval Test
completed, Oct 2024
H32CDF-LA dual-fuel (3.6–5.4 MW, marine)
Type Approval Test
completed, Oct 2025
Wärtsilä
25 Ammonia (1.9–3.1 MW, marine)
Skarv genset Q4 2026 &
Eidesvik ops start, end 2026
Navigator Amon
2nd ship, Sep 2027
2027
2028
2029
2030
2031
2032
GENTARI
Study → commercialisation pathway
1
1 mo
2
2 mo
3
4
6–9 mo (9)
5
~10 mo
6
7
~30 mo
8
~6 mo
Commercialisation
(target, assumption)
① Issue RFP — 1 month (input)
② Finalise bilateral agreement with OEM — 2 months (input)
③ Kickoff (input)
④ Pre-FEED study — 6–9 months, shown 9 (input)
⑤ FEED — ~10 months (assumption)
⑥ FID — Final Investment Decision (assumption)
⑦ EPC — engineering, procurement & construction — ~30 months (assumption)
⑧ Commissioning & start-up — ~6 months (assumption)
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Grey rows/bars/italic labels = AWS/research_OEM (public-search survey); coloured rows = AWS/comm_OEM (OEMs' own commercial decks — IHI→Gentari deck 27 Aug 2026; Wärtsilä→MISC deck 1 Sep 2026; HiMSEN ammonia engine deck).
Stars = indicative readiness/commercialisation date or milestone. Hatched bars (dashed border, lighter fill) = planned, uncertain, or unverified.
Gentari pathway (①–⑧): RFP timed to follow Wärtsilä ammonia-engine commercialisation (assumption). ①–④ are user-specified inputs; ⑤–⑧ are Claude-filled indicative assumptions (not sourced) — confirm in memory.md before use.