## Slide 1
Ammonia gas engine readiness timeline — IHI, HD Hyundai, Wärtsilä
MYSGH2 power-generation OEM survey — ammonia-fired reciprocating gas engines only (excludes hydrogen engines & gas turbines), plus Gentari's study-to-commercialisation pathway
OEM readiness (confirmed)
OEM readiness (target, unverified)
Planned / uncertain period
Tested / confirmed period
2023
2024
2025
2026
2027
2028
2029
Today, 18 Sep 2026
IHI
18V28ADF ammonia 4-stroke (6 MW)
Sales from JFY2027
HD Hyundai
HiMSEN ammonia genset (stationary)
intent stated, no date confirmed
Wärtsilä
25 Ammonia (1.9–3.1 MW)
2026?
or 2028?
2027
2028
2029
2030
2031
2032
GENTARI
Study → commercialisation pathway
1
1 mo
2
2 mo
3
4
6–9 mo (9)
5
~10 mo
6
7
~30 mo
8
~6 mo
Commercialisation
(target, assumption)
① Issue RFP — 1 month (input)
② Finalise bilateral agreement with OEM — 2 months (input)
③ Kickoff (input)
④ Pre-FEED study — 6–9 months, shown 9 (input)
⑤ FEED — ~10 months (assumption)
⑥ FID — Final Investment Decision (assumption)
⑦ EPC — engineering, procurement & construction — ~30 months (assumption)
⑧ Commissioning & start-up — ~6 months (assumption)
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Scope: ammonia-fired reciprocating gas engines only — excludes hydrogen-fired engines (Wärtsilä 31H2, HD Hyundai HiMSEN pure-H₂, Infracore 11L H₂) and ammonia gas turbines (IHI IM270, IHI+GE Vernova F-class).
Stars = indicative readiness/commercialisation date. Hatched bars (dashed border, lighter fill) = planned, uncertain, or unverified.
Gentari pathway (①–⑧): RFP timed to follow Wärtsilä ammonia-engine commercialisation (assumption). ①–④ are user-specified inputs; ⑤–⑧ are Claude-filled indicative assumptions (not sourced) — confirm in memory.md before use.