## Slide 1
Gas engine / turbine readiness timeline — IHI, HD Hyundai, Wärtsilä
MYSGH2 power-generation OEM survey — ammonia & hydrogen gensets/turbines, by OEM, plus Gentari's study-to-commercialisation pathway
OEM readiness (confirmed)
OEM readiness (target, unverified)
Planned / uncertain period
Tested / confirmed period
2020
2021
2022
2023
2024
2025
2026
2027
2028
2029
2030
2031
Today, 17 Sep 2026
IHI
IM270 ammonia GT (2 MW) — test → Terengganu
Commercial from 2027
18V28ADF ammonia 4-stroke (6 MW)
Sales from JFY2027
IHI + GE Vernova F-class (ammonia GT)
Target ~2030
HD Hyundai
HiMSEN pure-H₂ 4-stroke
Sales claim unverified
Infracore roadmap, 11L H₂ engine
Power-gen target 2026
HiMSEN ammonia genset (stationary)
intent stated, no date confirmed
Wärtsilä
25 Ammonia (1.9–3.1 MW)
2026?
or 2028?
31H2 / 31SG-H2 (4.6–10.4 MW)
100% H₂ grid test, Jun 2026
2027
2028
2029
2030
2031
2032
GENTARI
Study → commercialisation pathway
1
1 mo
2
2 mo
3
4
6–9 mo (9)
5
~10 mo
6
7
~30 mo
8
~6 mo
Commercialisation
(target, assumption)
① Issue RFP — 1 month (input)
② Finalise bilateral agreement with OEM — 2 months (input)
③ Kickoff (input)
④ Pre-FEED study — 6–9 months, shown 9 (input)
⑤ FEED — ~10 months (assumption)
⑥ FID — Final Investment Decision (assumption)
⑦ EPC — engineering, procurement & construction — ~30 months (assumption)
⑧ Commissioning & start-up — ~6 months (assumption)
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Stars = indicative readiness/commercialisation date. Hatched OEM bars (dashed border, lighter fill) = planned, uncertain, or unverified.
Gentari pathway (①–⑧): RFP timed to follow Wärtsilä commercialisation (assumption). ①–④ are user-specified inputs; ⑤–⑧ are Claude-filled indicative assumptions (not sourced) — confirm in memory.md before use.