## Task List
YTL x MYSGH2 - Ammonia 4-Stroke Gas Engine Study - Task List (master data)
Edit tasks here - the 'Gantt Chart' tab reads every field from this sheet via formulas, so changes to dates, workstream, type or owner update the Gantt bars and colors automatically.
ID | Task | Workstream | Type | Owner | Start | Finish | Duration (working days) | Predecessor(s)
P1 | Finalize OEM shortlist & confirm with MISC | Governance | Task | MYSGH2/MISC | 2026-08-17 | 2026-08-18 | 2 | -
P2 | Draft kickoff agenda & study charter | Governance | Task | MYSGH2 | 2026-08-17 | 2026-08-19 | 3 | -
P3 | Align data/evidence requirements to hand to MISC | OEM Engagement (MISC-led) | Task | MYSGH2 | 2026-08-18 | 2026-08-20 | 3 | P1
P4 | Confirm NDA status per OEM (via MISC) | OEM Engagement (MISC-led) | Task | MISC | 2026-08-19 | 2026-08-21 | 3 | P1
P5 | Internal YTL / MYSGH2 / MISC alignment call | Governance | Milestone | Both | 2026-08-21 | 2026-08-21 | 1 | P2, P3, P4
M1 | KICKOFF MEETING | Governance | Milestone | Both | 2026-08-25 | 2026-08-25 | 1 | P5
W1.1 | Agree Technology Risk Assessment framework skeleton | Technology Risk Assessment | Task | MYSGH2 | 2026-08-26 | 2026-08-27 | 2 | M1
W1.2 | Finalize workstream owners & roles | Governance | Task | Both | 2026-08-31 | 2026-08-31 | 1 | M1
OEM1 | OEM ENGAGEMENT & DATA COLLECTION (led by MISC) | OEM Engagement (MISC-led) | Task | MISC | 2026-08-31 | 2026-09-16 | 13 | M1, P4
W2.1 | Build Technology Risk Assessment framework v1 (maturity TRL/CRI scale + carbon-emission methodology) | Technology Risk Assessment | Task | MYSGH2 | 2026-09-01 | 2026-09-07 | 5 | W1.1
W2.2 | Weekly status check-in (Wk2) | Governance | Milestone | Both | 2026-09-04 | 2026-09-04 | 1 | OEM1
W3.1 | Populate Technology Risk Assessment scorecard (maturity + carbon, per OEM) | Technology Risk Assessment | Task | MYSGH2 | 2026-09-08 | 2026-09-11 | 4 | W2.1, OEM1
W3.2 | Draft performance-contract framework | Contract | Task | MYSGH2/YTL | 2026-09-10 | 2026-09-14 | 3 | OEM1
W3.3 | Weekly status check-in (Wk3) | Governance | Milestone | Both | 2026-09-11 | 2026-09-11 | 1 | W3.1
W4.1 | Build risk & derisking framework (fuel-supply, safety/toxicity, regulatory, counterparty) | Risk | Task | MYSGH2 | 2026-09-15 | 2026-09-17 | 3 | W3.1, W3.2
W4.2 | Consolidate all findings | Reporting | Task | MYSGH2 | 2026-09-17 | 2026-09-18 | 2 | W4.1, OEM1
W4.3 | Draft consolidated report | Reporting | Task | MYSGH2 | 2026-09-18 | 2026-09-21 | 2 | W4.2
W4.4 | Internal YTL review of draft report | Governance | Milestone | YTL | 2026-09-21 | 2026-09-21 | 1 | W4.3
F1 | Incorporate YTL review comments | Reporting | Task | MYSGH2 | 2026-09-22 | 2026-09-22 | 1 | W4.4
F2 | FINAL REPORT & CLOSE-OUT SESSION | Governance | Milestone | Both | 2026-09-22 | 2026-09-22 | 1 | F1
Formulas:
Duration (working days) = NETWORKDAYS([Start],[Finish])

## Gantt Chart
YTL x MYSGH2 - Ammonia 4-Stroke Gas Engine Study - Gantt Chart
Kickoff: Tue 25 Aug 2026 ¦ Finish: Tue 22 Sep 2026 ¦ Linked live to the 'Task List' tab - edit tasks there, this chart (incl. bar colors) updates automatically
ID | Task | Workstream | Type | Owner | Start | Finish | Duration (working days) | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22
P1 | Finalize OEM shortlist & confirm with MISC | Governance | Task | MYSGH2/MISC | 2026-08-17 | 2026-08-18 | 2
P2 | Draft kickoff agenda & study charter | Governance | Task | MYSGH2 | 2026-08-17 | 2026-08-19 | 3
P3 | Align data/evidence requirements to hand to MISC | OEM Engagement (MISC-led) | Task | MYSGH2 | 2026-08-18 | 2026-08-20 | 3
P4 | Confirm NDA status per OEM (via MISC) | OEM Engagement (MISC-led) | Task | MISC | 2026-08-19 | 2026-08-21 | 3
P5 | Internal YTL / MYSGH2 / MISC alignment call | Governance | Milestone | Both | 2026-08-21 | 2026-08-21 | 1
M1 | KICKOFF MEETING | Governance | Milestone | Both | 2026-08-25 | 2026-08-25 | 1
W1.1 | Agree Technology Risk Assessment framework skeleton | Technology Risk Assessment | Task | MYSGH2 | 2026-08-26 | 2026-08-27 | 2
W1.2 | Finalize workstream owners & roles | Governance | Task | Both | 2026-08-31 | 2026-08-31 | 1
OEM1 | OEM ENGAGEMENT & DATA COLLECTION (led by MISC) | OEM Engagement (MISC-led) | Task | MISC | 2026-08-31 | 2026-09-16 | 13
W2.1 | Build Technology Risk Assessment framework v1 (maturity TRL/CRI scale + carbon-emission methodology) | Technology Risk Assessment | Task | MYSGH2 | 2026-09-01 | 2026-09-07 | 5
W2.2 | Weekly status check-in (Wk2) | Governance | Milestone | Both | 2026-09-04 | 2026-09-04 | 1
W3.1 | Populate Technology Risk Assessment scorecard (maturity + carbon, per OEM) | Technology Risk Assessment | Task | MYSGH2 | 2026-09-08 | 2026-09-11 | 4
W3.2 | Draft performance-contract framework | Contract | Task | MYSGH2/YTL | 2026-09-10 | 2026-09-14 | 3
W3.3 | Weekly status check-in (Wk3) | Governance | Milestone | Both | 2026-09-11 | 2026-09-11 | 1
W4.1 | Build risk & derisking framework (fuel-supply, safety/toxicity, regulatory, counterparty) | Risk | Task | MYSGH2 | 2026-09-15 | 2026-09-17 | 3
W4.2 | Consolidate all findings | Reporting | Task | MYSGH2 | 2026-09-17 | 2026-09-18 | 2
W4.3 | Draft consolidated report | Reporting | Task | MYSGH2 | 2026-09-18 | 2026-09-21 | 2
W4.4 | Internal YTL review of draft report | Governance | Milestone | YTL | 2026-09-21 | 2026-09-21 | 1
F1 | Incorporate YTL review comments | Reporting | Task | MYSGH2 | 2026-09-22 | 2026-09-22 | 1
F2 | FINAL REPORT & CLOSE-OUT SESSION | Governance | Milestone | Both | 2026-09-22 | 2026-09-22 | 1

## Legend
Legend
| Workstream / Type | Description
| Milestone | Gold diamond marker - a decision point, checkpoint, or deliverable hand-off (single day, zero-duration in effect)
| Governance | Kickoff, status check-ins, internal YTL/MYSGH2/MISC alignment and sign-off
| OEM Engagement (MISC-led) | MISC (parent-company partner with existing OEM contacts) owns all direct OEM engagement - one continuous item covering introductions, data collection, follow-ups and Q&A, rather than separate MYSGH2-run RFI/discussion rounds
| Technology Risk Assessment | Merged maturity (TRL/CRI-style scale) + carbon-emission methodology (incl. N2O/GWP273, NOx, NH3 slip) assessment and per-OEM scorecard
| Contract | Performance-contract framework: availability, heat-rate/efficiency, emissions guarantees, LDs, warranty
| Risk | Risk & derisking framework: fuel-supply, safety/toxicity, regulatory, counterparty risk (technology risk lives in Technology Risk Assessment above)
| Reporting | Findings consolidation, draft and final report production
Notes
- The 'Gantt Chart' tab is fully formula-linked to 'Task List': every column (Task, Workstream, Type, Owner, Start, Finish, Duration) is a direct cell reference, and the bar colors are Conditional Formatting rules keyed off those same linked cells - so editing a row in Task List (incl. dragging dates) updates the chart and its colors automatically. Do not type directly into the Gantt Chart tab's task columns; edit Task List instead.
- Working days only (Mon-Fri); weekends are compressed out of the day-column grid.
- Duration column uses =NETWORKDAYS(Start,Finish).
- OEM engagement is run by MISC (our partner company under the parent group, which holds the OEM relationships) as ONE continuous item/timeline - not broken into MYSGH2-run RFI or discussion-round sub-tasks.
- Maturity and carbon-emission assessment are merged into a single 'Technology Risk Assessment' workstream.
- This is a proposed schedule (per CLAUDE.md No-Fabrication Rule: a plan, not a sourced technical claim). The OEM Engagement item's dates are MYSGH2's planning assumption for when MISC's outreach needs to complete to feed the Technology Risk Assessment - confirm actual cadence with MISC.
- Source: MYSGH2 project, drafted 2026-08-14, revised 2026-08-14 (OEM engagement routed through MISC; maturity+carbon merged into Technology Risk Assessment; Task List linked live to Gantt Chart).